## Sheet1
| Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Build Preprocessing Module | Alex
Set up SQL database | Josh
Build Network Model in Keras |  | Alex
Dowload and Add Dataset to Database |  | Josh
Preprocess Database |  |  |  | Both
First Training Process |  |  |  |  | Both
GAN Tweaking | [5 empty] | Both
Finalize GAN | [10 empty] | Both
Prepare Findings | [10 empty] | Both